## Inbound
Dress Changes Style 구축 일정 (WBS)
PM : Max, Pralhad | Plan Color
Completion Color
Work Breakdown Structure | [6 empty] | April | [15 empty] | May | [30 empty] | June | [30 empty] | July | [14 empty] | Remarks
Phase | Activity |  | Start Date | End Date | Completed | Manager | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Planning | Working list / WBS write | 업무 리스트 및 WBS 작성 | 2019-04-16 | 2019-04-16 |  | Max
| Function list / Policy definition | 기능 및 정책 정의서 작성
| Schedule output meeting | 일정 산출 회의 | 2019-04-16 | 2019-04-16 |  | M/P/S
| Schedule output | 일정 산출 | 2019-04-16 | 2019-04-16 |  | M/P/S
| Story board write | 화면정의서(스토리보드) 작성
Development (Core API) | Core API Development |  | 2019-04-10 | 2019-05-15
| Authentication Module | 인증 모듈 | 2019-04-15 | 2019-04-15 |  | Saroj
| Exchange Rate Module | 환율 모듈 | 2019-04-15 | 2019-04-15 |  | Saroj
| Send Transaction Module | 전송 모듈 | 2019-04-16 | 2019-04-17 |  | Saroj
| Commit Transaction Module | 확인 모듈 | 2019-04-17 | 2019-04-17 |  | Saroj
| Check Status Module | 상태 체크 모듈 | 2019-04-18 | 2019-04-18 |  | Saroj
| Cancel Request Module | 취소 모듈 | 2019-04-18 | 2019-04-18 |  | Max
| Amendment request Module | 수정 모듈 | 2019-04-19 | 2019-04-19 |  | Saroj
| Get Static Value |  | 2019-04-22 | 2019-04-22 |  | Pralhad
| Secuity Module | 보안 모듈 | 2019-04-23 | 2019-04-24 |  | Saroj/Pralhad
| AML Screening | 자금세탁방지 모듈 | 2019-04-25 | 2019-04-25 |  | Saroj
| Credit Limit checking for page (checking only from accounting) | 신용한도 체크모듈 | 2019-04-25 | 2019-04-26 |  | Saroj
| API Document Making | API 문서 제작 | 2019-04-15 | 2019-04-30 |  | M/P/S
| RIA Providing for Test-Bed | 테스트베드 제공(RIA) | 2019-05-13 | 2019-05-15 |  | Max/Pralhad
Development (Core Module) | Core Module for Remittance System |  | 2019-04-29 | 2019-06-21
| Exchange Rate Setup page | 환율 환경 설정 | 2019-04-29 | 2019-05-07 |  | Pralhad/Max
| Comission Setup page | 수수료 환경 설정 | 2019-04-29 | 2019-05-07 |  | Pralhad/Max
| Accounting Voucher Setup - Voucher Generation - Exchange Gain/Loss Calculation | 전표 환경 설정 - 전표 일반 - | 2019-04-29 | 2019-05-07 |  | Pralhad/Max
| Hold txn approve page |  | 2019-05-08 | 2019-05-09 |  | Pralhad/Max
| Cancellation/amendment page |  | 2019-05-10 | 2019-05-15 |  | Saroj
| Deposit Money in receiver's a/c using KJ Bank - UI (Manual) | 계좌입금(고객)-수동방식 | 2019-05-16 | 2019-05-20 |  | Pralhad/Max
| Deposit Money in receiver's a/c using KJ Bank - Scheduling (Auto) | 계좌입금(고객)-자동방식 | 2019-05-21 | 2019-05-22 |  | Pralhad/Max
| Compliance Checking - USD 5000 per txn, USD 50,000 per year | 연간한도체크 | 2019-05-23 | 2019-05-24 |  | Pralhad/Max
| Duplicate Receiver Identifier | 중복 수신 식별 | 2019-05-27 | 2019-05-27 |  | Pralhad/Max
| Credit Limit Setup and Checking for partner - Partner OD Limit Setup - Top-up Setup- Checker and Maker - Topup History - Per txn limit - Daily limit - Annual Limit |  | 2019-05-28 | 2019-06-11 |  | Pralhad/Max
| Report - Send Txn Report( country wise/partnerwise Matrix) - Cancel Txn Report(( country wise/partnerwise Matrix) - Settlement Report For partner - BOK Report |  | 2019-06-10 | 2019-06-21 |  | Saroj
Development (Online) | Inbound development in Online-https://online.gmeremit.com/inboundkyc/? |  | 2019-06-07 | 2019-06-27
| Registration & KYC Document upload |  | 2019-06-07 | 2019-06-11 |  | Ryan/Pralhad
| Penny Test |  | 2019-06-12 | 2019-06-13 |  | Ryan/Max
| -Dashboard |  | 2019-06-14 | 2019-06-17 |  | Saroj
| -Inbound Txn History |  | 2019-06-18 | 2019-06-19 |  | Ryan/Saroj
| -Add Bank Account |  | 2019-06-19 | 2019-06-20 |  | Saroj/Max
| -Add missing information to Send Txn |  | 2019-06-21 | 2019-06-24 |  | Saroj/Pralhad
| -Edit Customer Profile |  | 2019-06-25 | 2019-06-27 |  | Pralhad/Max
Development (Mobile API) | Inbound Development in Mobile app (API) |  | 2019-06-07 | 2019-06-26
| -Dashboard |  | 2019-06-07 | 2019-06-10 |  | Saroj
| -Inbound Txn History |  | 2019-06-11 | 2019-06-12 |  | Saroj
| -Add Bank Account |  | 2019-06-18 | 2019-06-19 |  | Saroj/Max
| -Add missing information to Send Txn |  | 2019-06-20 | 2019-06-21 |  | Saroj/Pralhad
| -Edit Customer Profile |  | 2019-06-24 | 2019-06-26 |  | Pralhad/Max
Development (Mobile App) | Inbound Development in Mobile app (iOS/Android) |  | 2019-06-03 | 2019-06-28
| -Dashboard |  |  | 2019-06-28 |  | James/New
| -Inbound Txn History |  |  | 2019-06-28 |  | James/New
| -Add Bank Account |  |  | 2019-06-28 |  | James/New
| -Add missing information to Send Txn |  |  | 2019-06-28 |  | James/New
| -Edit Customer Profile |  |  | 2019-06-28 |  | James/New
Test | Inbound Test |  | 2019-04-29 | 2019-07-12
| API Functional Testing (local) |  | 2019-04-29 | 2019-05-03 |  | M/P/S
| Partner(RIA) Providing for Test-Bed Testing |  | 2019-05-07 | 2019-05-10 |  | M/P/S
| Core Setup Testing |  | 2019-06-24 | 2019-06-28 |  | Max/Pralhad
| Online Module Testing |  | 2019-07-01 | 2019-07-05 |  | Ryan/Saroj
| Mobile API Testing |  | 2019-07-01 | 2019-07-05 |  | M/P/S
| Mobile APP Testing |  | 2019-07-01 | 2019-07-05 |  | App Developer
| Integration Testing |  | 2019-07-08 | 2019-07-12 |  | App Developer
Publish | Publish | 배포(라이브) | 2019-07-15 | 2019-07-15 |  | Pralhad/Max