## Sprint plan
SN | Product Backlog item | Tasks | Team required | Estimated days
1 | Invite a friend | API endpoint development | Backend | 1
|  | Invite friend Screen design and development | Mobile | 2
|  | Endpoint test | QA | 0.5
2 | Share invitation link | API endpoint development | Backend | 1
|  | Share invitation Screen design and development | Mobile | 2
|  | Endpoint test | QA | 0.5
3 | Reward page | API endpoint development | Backend | 1
|  | Reward Screen design and development | Mobile | 2
|  | Endpoint test | QA | 0.5
4 | Invite status | API endpoint development | Backend | 1
|  | Invite status Screen design and development | Mobile | 2
|  | Endpoint test | QA | 0.5
5 | Spin the wheel | API integration | Backend | 1
|  | Spin wheel Screen design and development | Mobile | 2
|  | test | QA | 1
6 | Overall app test | Test the Referral module | QA | 3