## Sheet1
B2B Project Requirement List & Schedule
Dec-14(Tue) by Max
분류 | 메뉴명 | 설명 | Design | Development | Test & Fix
Setup | Static Data | Currency Code, Bank Code, Customer Type,...
| Data Encrypt |  | 2 | 3 | 2
| Setup Exchange Rate |  | 3 | 3 | 3
| Setup Service Charge |  | 3 | 3 | 3
| Total |  | 8 | 9 | 8 | 25
Partner Management | Create/Update/Delete Partner |  | 3 | 5 | 3
| List of Partners |  | 2 | 2 | 2
| Details of Partner |  | 2 | 2 | 2
| Total |  | 7 | 9 | 7 | 23
Token Management | Token Issue | Token Issue /Verification | 3 | 3 | 2
| List of Tokens | Token Issuance History | 2 | 2 | 1
| Total |  | 5 | 5 | 3 | 13
Fund Management | Get FX Rate |  | 3 | 5 | 3
| Exchange Fund | USD to KRW | 3 | 5 | 3
| Create/Confirm Deposit |  | 3 | 5 | 3
| List of Deposit History |  | 2 | 3 | 2
| Balance Management |  | 2 | 3 | 2
| Total |  | 13 | 21 | 13 | 47
Member Management | Create/Update Member |  | 2 | 3 | 2
| List of Members |  | 2 | 2 | 1
| Total |  | 4 | 5 | 3 | 12
Payout Management | Create Transfer |  | 3 | 3 | 2
| List of Transfer |  | 2 | 2 | 2
| Total |  | 5 | 5 | 4 | 14
Account Management | Create Voucher |  | 3 | 3 | 2 | 8
Inbound API | Authentication
Calculate Exchange Rate
Create Transaction
Commit Transaction
Modify Transaction
Cancel Transaction
Check Transaction Status
| Total |  | 5 | 10 | 5 | 20
KFTC API | 사용자 인증 API
토큰 발급 API
토큰 폐기 API
서비스 등록확인 API
사용자 정보조회 API
사용자 로그인 연결동의 해제 API
등록계좌조회 API
계좌정보변경 API(센터인증)
계좌해지 API
사용자탈퇴 API
잔액조회 API
거래내역조회 API
계좌실명조회 API
수취조회 API
출금이체 API
입금이체 API
이체결과조회 API
자금반환청구 API
자금반환청구 결과조회 API
| Total |  | 7 | 15 | 7 | 29
Partner DashBoard | Login
Partner Details
Balance History
Deposit History
Confirm Balance
Search Transaction
Transaction List
Transaction Details
Notification List
| Total |  | 5 | 10 | 5 | 20
211

## Sheet2
B2B Project Assign Task
Dec-14(Tue) by Max
분류 | 메뉴명 | 설명 | Design | Development | Test & Fix
Setup | Static Data | Currency Code, Bank Code, Customer Type,...
| Data Encrypt |  | Manoj | Ram
| Setup Exchange Rate |  | Saroj | Ram
| Setup Service Charge |  | Manoj | Ram
| Total |  | 8 | 9 | 8
Partner Management | Create/Update/Delete Partner |  | Manoj | Dhan | 3
| List of Partners |  | Manoj | Dhan | 2
| Details of Partner |  | Manoj | Dhan | 2
| Total |  | 7 | 9 | 7
Token Management | Token Issue | Token Issue /Verification | Saroj | Dhan | 2
| List of Tokens | Token Issuance History | Saroj | Dhan | 1
| Total |  | 5 | 5 | 3
Fund Management | Get FX Rate |  | Saroj | Dhan | 3
| Exchange Fund | USD to KRW | Saroj | Dhan | 3
| Create/Confirm Deposit |  | Saroj | Dhan | 3
| List of Deposit History |  | Saroj | Dhan | 2
| Balance Management |  | Saroj | Dhan | 2
| Total |  | 13 | 21 | 13
Member Management | Create/Update Member |  | Manoj | Dhan | 2
| List of Members |  | Manoj | Dhan | 1
| Total |  | 4 | 5 | 3
Payout Management | Create Transfer |  | Manoj | Dhan | 2
| List of Transfer |  | Manoj | Dhan | 2
| Total |  | 5 | 5 | 4
Account Management | Create Voucher |  | Saroj | Dhan | 2
Inbound API | Authentication |  | Saroj | Ram
| Calculate Exchange Rate |  | Saroj | Ram
| Create Transaction |  | Saroj | Ram
| Commit Transaction |  | Saroj | Ram
| Modify Transaction |  | Saroj | Ram
| Cancel Transaction |  | Saroj | Ram
| Check Transaction Status |  | Saroj | Ram
| Total |  | 5 | 10 | 5
KFTC API | 사용자 인증 API |  | Max | JY
| 토큰 발급 API |  | Max | JY
| 토큰 폐기 API |  | Max | JY
| 서비스 등록확인 API |  | Max | JY
| 사용자 정보조회 API |  | Max | JY
| 사용자 로그인 연결동의 해제 API |  | Max | JY
| 등록계좌조회 API |  | Max | JY
| 계좌정보변경 API(센터인증) |  | Max | JY
| 계좌해지 API |  | Max | JY
| 사용자탈퇴 API |  | Max | JY
| 잔액조회 API |  | Max | JY
| 거래내역조회 API |  | Max | JY
| 계좌실명조회 API |  | Max | JY
| 수취조회 API |  | Max | JY
| 출금이체 API |  | Max | JY
| 입금이체 API |  | Max | JY
| 이체결과조회 API |  | Max | JY
| 자금반환청구 API |  | Max | JY
| 자금반환청구 결과조회 API |  | Max | JY
| Total |  | 7 | 15 | 7
Partner DashBoard | Login |  | Manoj | Ram
| Partner Details |  | Manoj | Ram
| Balance History |  | Manoj | Ram
| Deposit History |  | Manoj | Ram
| Confirm Balance |  | Manoj | Ram
| Search Transaction |  | Manoj | Ram
| Transaction List |  | Manoj | Ram
| Transaction Details |  | Manoj | Ram
| Notification List |  | Manoj | Ram
| Total |  | 5 | 10 | 5