## Sheet1
Task Priority
Fix existing issues, Bugs ,double refund cases
New Developments
New Partner API

## Sheet2
1 | Cashbee
Cashbee Auto Recharge
Cashbee Notification
Cashbee iOS
2 | KFTC | [7 empty] | Zeropay?
|  | KFTC Self Certification with Gmoney method | [6 empty] | Bill payment?
|  | KFTC Self Certification with Coinshot method | [6 empty] | Show all limit?
3 | Receiver Initiated Inbound
|  | Receiver Initiated Inbound Vietnam | [6 empty] | Alipay QR code
Receiver Initiated Inbound Mongolia
4 | Register GME on Zalo
Easy remit customer registration via Zalo
1) OCR + Face recognition via Comtrue
5 | Homepage renewal
New homepage design
6 | Hyperlink inside add
If no balance in wallet --> ask to register autodebit
7 | New registration process (easy + normal)
| Corridor | IT problems/ support requests | PIC | Issue Raised On | Days Since issue raised | Target to be solved on | Issue solved on | Remark
|  | No of It Issues |  | 18
1 | General | Show limit and payout time while calculating ex rate before sending transaction (In case of customer reached monthly or daily limits, app should show balance of montly /daily limits for all users in the error's popup msg and guide of when can they start to transfer again both local transfer and oversae transfer) | Manoj | 2022-04-28 | 481 | 2023-03-28 |  | Cancelled and need to restart the project 2023-02-02: Waiting for the confirmation for compliance team
2 | General | NH Auto debit issue for some customers | Boren |  | Waiting for boren |  |  | Waiting for boren to send us some cases (First complaint date: 2022-08-02)
3 | General | Group report is not working properly- data is not accurate (transaction and registration) | Manoj | 2022-12-01 | 264 | 2023-02-14 |  | 2023-02-02: To-be tested after publish 2023-04-03: Planning to Published
4 | General | Registration report - 1st transaction data is not accurate |  | 2022-12-01 | 264 | 2023-02-14 |  | 2023-02-02: To-be tested after publish 2023-04-03: Planning to Published
5 | Cambodia | In bank deposit menu, if customer select wing bank, route transactions to Wing wallet (partner wing - wallet deposit) | Boren | 2022-12-29 | Cancelled by Boren |  | 2023-03-02
6 | Myanmar | Payment method translation is wrong in mobile | Manoj | 1/12/2023 | Solved |  | 2023-01-26
7 | General | While exporting reports to excel, it should export all results from DB. not only 1000 which shows in the front page | Sagar | 2023-02-22 | 181 | 2023-03-30 |  | (2023-01-26)) There are too many report menus. We need to decide the report menu. When the report menu is decided, the development will begin. Issue Raised Date should be the date after decide report menu. [Menu] Remittance>>report master>>Transaction Report master Remittance>>reports>>Transaction/Registration Reports Remittance>>reports>>native country wise txn report Remittance>>reports>>Transaction/Registration group Report [2302-15] Export Report to Excel
8 | General | Add API logs for all partners in API log table in core system (start with ria) KoronaPay Thunes TerraPay BNI BOP Tranglo | Subash | 2023-01-12 | 222 | 2023-02-28 |  | Project created [2302-03] Add Missing API logs in Core
9 | General | User should not be logged out if there is any network issue from user's side or gme side | Dhan | 2023-01-19 | 215 | 2023-02-28 |  | Santosh is researching on it [2302-05] Change Logging Out Rule of Mobile App
10 | Cambodia | Consider bank deposit transactions as paid after successfully posted | Pujan | 2023-01-26 | 208 | 2023-02-26 |  | [2302-08] Change Payment Status on Cambodia Txn 2023-03-09: Development completed. will be published togather with realname issue fixing
11 | Cambodia | Wing: when partner cancel cash deposit transaction, it should be cancelled automatically in GME. Need to check API. If dont't have call back api, cancel the project | Boren |  |  |  |  | Waiting for boren to send us API document
12 | General | Customer doesn't receive emails after reset password and find user ID | Dhan | 2023-02-02 | Solved | 2023-03-02 | 2023-04-03 | [2302-10] Change Email Module 2023-04-03: Published
13 | General | Used store coupons availble in the "available" tab in mobile - New history - coupon | Manoj | 2023-02-02 | 201 | 2023-03-02 |  | feedback project
14 | General | Store deposit: Even when the existing request passes 10 mins, user cannot request for new deposit request.. | Nepal Subash |  | Removed as there are no any new cases |  |  | Case reported: 2023-02-09 IT tried to recreate it, but it is not being recreated. If this phenomenon is found, please show the video.
15 | Cambodia | Automatic email request to wing partner if cancel request from mobile and Core system. | Rajesh
16 | General | Show only available payment method in today's rate for correnspondant currency | Max | 2023-03-09 | 166
17 | General | In today's menu, default currency should be setup from core system | Max | 2023-03-09 | 166
19 | General | Add control number filter in Local topup search menu | Sagar | 2023-03-23 | 152
20 |  | Add Column in approve holded txn menu |  | 2023-03-30 | 145
21 |  | Seperate GIBL deposit transaction report in Report ->vReport master |  | 2023-03-30 | 145
22 |  | iOS: When open app for the first time, default language is Myanmar language. (it should be English) | Manish | 2023-03-30 | 145
23 |  | iOS: Russian language doesn't work before login to app |  | 2023-03-30 | 145
24 |  | Android: Cashbeee balance is different in (monthly recharge-use) and actual balance |  | 2023-03-30 | 145
25 |  | Koronapay Inbound issue
Formulas:
Days Since issue raised = IF([Issue solved on]>0,"Solved",TODAY()-[Issue Raised On])

## IT Issue List
| Corridor | IT problems/ support requests | PIC | Issue Raised On | Days Since issue raised | Target to be solved on | Issue solved on | Remark
|  | No of It Issues |  | 18
1 | General | Show limit and payout time while calculating ex rate before sending transaction (In case of customer reached monthly or daily limits, app should show balance of montly /daily limits for all users in the error's popup msg and guide of when can they start to transfer again both local transfer and oversae transfer) | Manoj | 2022-04-28 | 481 | 2023-03-28 |  | Cancelled and need to restart the project 2023-02-02: Waiting for the confirmation for compliance team
2 | General | NH Auto debit issue for some customers | Boren |  | Waiting for boren |  |  | Waiting for boren to send us some cases (First complaint date: 2022-08-02)
3 | General | Group report is not working properly- data is not accurate (transaction and registration) | Manoj | 2022-12-01 | 264 | 2023-02-14 |  | 2023-02-02: To-be tested after publish 2023-04-03: Planning to Published
4 | General | Registration report - 1st transaction data is not accurate |  | 2022-12-01 | 264 | 2023-02-14 |  | 2023-02-02: To-be tested after publish 2023-04-03: Planning to Published
5 | Cambodia | In bank deposit menu, if customer select wing bank, route transactions to Wing wallet (partner wing - wallet deposit) | Boren | 2022-12-29 | Cancelled by Boren |  | 2023-03-02
6 | Myanmar | Payment method translation is wrong in mobile | Manoj | 1/12/2023 | Solved |  | 2023-01-26
7 | General | While exporting reports to excel, it should export all results from DB. not only 1000 which shows in the front page | Sagar | 2023-02-22 | 181 | 2023-03-30 |  | (2023-01-26)) There are too many report menus. We need to decide the report menu. When the report menu is decided, the development will begin. Issue Raised Date should be the date after decide report menu. [Menu] Remittance>>report master>>Transaction Report master Remittance>>reports>>Transaction/Registration Reports Remittance>>reports>>native country wise txn report Remittance>>reports>>Transaction/Registration group Report [2302-15] Export Report to Excel
8 | General | Add API logs for all partners in API log table in core system (start with ria) KoronaPay Thunes TerraPay BNI BOP Tranglo | Subash | 2023-01-12 | 222 | 2023-02-28 |  | Project created [2302-03] Add Missing API logs in Core
9 | General | User should not be logged out if there is any network issue from user's side or gme side | Dhan | 2023-01-19 | 215 | 2023-02-28 |  | Santosh is researching on it [2302-05] Change Logging Out Rule of Mobile App
10 | Cambodia | Consider bank deposit transactions as paid after successfully posted | Pujan | 2023-01-26 | 208 | 2023-02-26 |  | [2302-08] Change Payment Status on Cambodia Txn 2023-03-09: Development completed. will be published togather with realname issue fixing
11 | Cambodia | Wing: when partner cancel cash deposit transaction, it should be cancelled automatically in GME. Need to check API. If dont't have call back api, cancel the project | Boren |  |  |  |  | Waiting for boren to send us API document
12 | General | Customer doesn't receive emails after reset password and find user ID | Dhan | 2023-02-02 | Solved | 2023-03-02 | 2023-04-03 | [2302-10] Change Email Module 2023-04-03: Published
13 | General | Used store coupons availble in the "available" tab in mobile - New history - coupon | Manoj | 2023-02-02 | 201 | 2023-03-02 |  | feedback project
14 | General | Store deposit: Even when the existing request passes 10 mins, user cannot request for new deposit request.. | Nepal Subash |  | Removed as there are no any new cases |  |  | Case reported: 2023-02-09 IT tried to recreate it, but it is not being recreated. If this phenomenon is found, please show the video.
15 | Cambodia | Automatic email request to wing partner if cancel request from mobile and Core system. | Rajesh
16 | General | Show only available payment method in today's rate for correnspondant currency | Max | 2023-03-09 | 166
17 | General | In today's menu, default currency should be setup from core system | Max | 2023-03-09 | 166
19 | General | Add control number filter in Local topup search menu | Sagar | 2023-03-23 | 152
20 |  | Add Column in approve holded txn menu |  | 2023-03-30 | 145
21 |  | Seperate GIBL deposit transaction report in Report ->vReport master |  | 2023-03-30 | 145
22 |  | iOS: When open app for the first time, default language is Myanmar language. (it should be English) | Manish | 2023-03-30 | 145
23 |  | iOS: Russian language doesn't work before login to app |  | 2023-03-30 | 145
24 |  | Android: Cashbeee balance is different in (monthly recharge-use) and actual balance |  | 2023-03-30 | 145
25 |  | Koronapay Inbound issue
Formulas:
Days Since issue raised = IF([Issue solved on]>0,"Solved",TODAY()-[Issue Raised On])

## 2023.03.23
IT Development Priority List 2023 Q2&Q3 |  | Feedback project
SN | Tasks | Gme project name |  | IT Target | Make Schedule | Tentative Start Date | Tentative Publish Date
1 | Cashbee Auto Recharge | [2303-03] Cashbee Card using GME Pay v2.0 | publish done | 2023-03-07 | Done
2 | Cashbee Notification: When customer use subway notification should be sent to GMEapp | [2303-03] Cashbee Card using GME Pay v2.0 | publish done | 2023-04-13 | Done
3 | Zero Pay | [2110-18] Zeropay in Mobile App | Stag testing finished | 2023-08-29 | can
4 | Bill Payment | [2209-16] Bill Payment using Sampath Bank [2301-12] Bill Payment History(Mobile, Core) | publish done |  | Done
5 | KFTC Self Certification with Gmoney method | [2207-01]KFTC Self Certification [2210-09] Raon PKI API [2211-22] KFTC Security Testing v2.1 | publish done |  | Done
6 | KFTC Self Certification with Coinshot method | [2304-13] KFTC Self Certification v2.0 | Planning on going | 2023-09-30 | can
7 | Fix the Easypromos issues: second name Null issue; point now shown in app, even though customer won the point | Feedback project | Second name null issue: Assigned to Subash but not finished yet 2023-04-20: send name null issue fixed | 2023-04-07 | can
8 | Receiver Initiated Inbound Vietnam | [2301-08] New Type Inbound Service | 1st Phase done. 2nd phase ongoing | 2023-08-29 | can
9 | Receiver Initiated Inbound Mongolia | [2306-17] New Type Inbound Service-Mongolia | Development on going | 2023-08-29 | can
10 | GME Check Card | [2306-09] GME Card Payment | Development on going | 2023-12-16 | can
11 | Easy remit customer registration via Zalo (OCR + Face recognition via Comtrue) | [2307-10] Easy remit registration using Zalo | Planning on going | 2023-09-30 | research
12 | Divert customers to corresponding CS according the chosen language |  | checking with channelTalk | 2023-08-29 | can
13 | Hyperlink inside app (If no balance in wallet --> ask to register autodebit) | [2304-14] Hyperlink Inside App | waiting for subash's requirement |  | cannot
14 | Group report is not working properly- data is not accurate (transaction and registration) | Feedback project | publish done |  | Done | still data is not accurate
15 | Add beneficiary using QR-Alipay |  | publish done |  | Done
16 | Octa Solution implementation | [2207-11] Setup AML Solution | Need to change Current logic |  | Done
17 | Macro Recon for partner and Bank Recon | [2306-12] Automatic Reconciliation | Publishing on going | 2023-08-14 | can
18 | New Homepage design | [2204-02] Change Main Page in Mobile App | publish done |  | Done
19 | Register customer device; if detect device change, ask for more questions (DOB, choose receiver and etc) | [2306-08] User Device Registration | Planning on going | 2023-09-30 | Can | research
20 | Remove OTP (replace OTP with simple PW) | [2306-15] Change OTP to Simple PW | Will be done after device registration finish | 2023-10-30 | cannot
21 | Merchants Platform for B2B |  |  |  | cannot
22 | New Core Admin System for B2B |  |  |  | cannot
23 | Registration report - 1st transaction data is not accurate | Feedback project | publish done |  | Done
24 | Koronapay Inbound issue | [2302-11] Fix Inbound Issue in Korona | Publish done |  | Done
25 | In bank deposit menu, if customer select wing bank, route transactions to Wing wallet (partner wing - wallet deposit) |  | Cancelled |  | Cancelled | Cancelled
26 | Payment method translation is wrong in mobile | Feedback project | publish done |  | Done
27 | While exporting reports to excel, it should export all results from DB. not only 1000 which shows in the front page | [2302-15] Export Report to Excel | publish done |  | Done | 2023-05-12: Checked by Sundariya. still data is wrong
28 | Add API logs for all partners in API log table in core system (start with ria) KoronaPay Thunes TerraPay BNI BOP Tranglo | [2302-03] Add Missing API logs in Core | BOP Published -> need to fix TerraPay to be published | 2023-08-30 | can
29 | User should not be logged out if there is any network issue from user's side or gme side | [2302-05] Change Logging Out Rule of Mobile App | publish done |  | Done
30 | Consider bank deposit transactions as paid after successfully posted | [2302-08] Change Payment Status on Cambodia Txn | publish done |  | can
31 | Wing: when partner cancel cash deposit transaction, it should be cancelled automatically in GME. Need to check API. If dont't have call back api, cancel the project | [2302-16] Cancel Wing Cash-Payment with Callback |  |  | Cancelled
32 | Customer doesn't receive emails after reset password and find user ID | [2302-10] Change Email Module | Publish done |  | Done
33 | Cancellation Email to partner via API ( Borens requirement) | Project not created | Publish done |  | Done
34 | Used store coupons availble in the "available" tab in mobile - New history - coupon | Feedback project | publish done |  | Done
35 | Store deposit: Even when the existing request passes 10 mins, user cannot request for new deposit request.. | Now there are no new cases | Cancelled |  | Cancelled
36 | Automatic email request to wing partner if cancel request from mobile and Core system. | [2304-06] Modify Approve hold transaction menu | Publish done |  | Done
37 | Show only available payment method in today's rate for correnspondant currency |  | Publish done |  | Done
38 | In today's menu, default currency should be setup from core system |  | Publish done | 2023-08-04
39 | Add control number filter in Local topup search menu | [2303-13] Bug fixing in Domestic topup search menu | Publish done |  | Done
40 | Add Column in approve holded txn menu | [2304-06] Modify Approve hold transaction menu | Publish done |  | Done
41 | Separate GIBL deposit transaction report in Report ->Report master | Feedback project | Publish done |  | Done
42 | iOS: When open app for the first time, default language is Myanmar language. (it should be English) | Feedback project | Publish done |  | Done
43 | iOS: Russian language doesn't work before login to app | Feedback project | Publish done |  | Done
44 | Android: Cashbeee balance is different in (monthly recharge-use) and actual balance | Feedback project | Nothing can be done from our side. Partner is checking |  | Cannot
45 | Cashbee iOS | [2306-09] GME Card Payment | Planning on going |  | can
46 | New registration process (easy + normal) | [2306-07] New user registration | need to disscuss with mt |  | can
47 | Show Revenue wise report to Marketing heads based on their country only |  | need to make design |  | can
48 | Send Bulk SMS in native language |  |  |  | cannot | research
49 | Kakaotalk integration for informing txn status (copy Sentbe) |  |  |  | cannot | research
50 | Service Charge and Pay commission Based on Multiple payout currency (dynamic service charge setup) | [2205-26] Setup Service Charge and Pay Commission in Core |  |  | can
51 | Pay commission calculation based on payout amount (dynamic pay commission setup) | [2205-28] Pay commission calculation base on payout amount |  |  | can
52 | Create 2 Popup pages in Mobile app which can be configurable by country wise, Receiving Country Wise, Partnerwise etc | [2308-01] Dynamic popup module |  |  | cannot | research
53 | QR ticketing function in Mobile App |  |  |  | cannot
54 | Using Hi Korea for auto approval of new customers |  |  |  | cannot
55 | Make a New table to calculate the Annual limit for USD 50,000 for both Inbound/Outbound | [2210-13] Change Inbound/Outbound 50000 USD Limit Checking | need to check and design |  | can
56 | Payout time while calculating ex rate before sending transaction | [2307-11] Show payout time in mobile and core | need to dev design and assign to developer |  | can | research
57 | Show the txn limit (1-time limit, 1-day limit, Yearly limit( while calculating ex rate) | [2209-05] Show All Limit in Mobile App | Publish done |  | Done
58 | Allow Schedule payment adding from Core system by GME Staff | [2111-08] Schedule Payment | need to publish |  | done
59 | Create special coupon for particular bank account (charity) | Already done | publish done |  | Done
60 | Auto checking phone carrier for both internation and domestic phon top up | Feedback project | publish done |  | Done
61 | Sendmn QRPay integration |  |  |  | cannot
62 | IME QRPay integration | [2208-18] Global QR Payment with IMEPay |  |  | cannot
63 | KakaoPay QR integration |  |  |  | cannot
64 | Allow to add beneficiary using QR Code to Send Money e.g. Alipay Beneficiary QR | [2306-06] Add recipient using QR (Alipay) | Publish done |  | Done
65 | Wechat API | [2210-26] WeChat Wallet Service for China | Publish done |  | Done
66 | Smartswift API | [2210-02] Smart-Swif33 Inbound API | Development on going |  | can
67 | Ipay remit inbound and outbound API | No project |  |  | cannot
68 | Alif bank inbound API | [2204-04] Alif Bank API | Development on going |  | can
69 | IME London inbound and outbound API |  |  |  | cannot
70 | Alipay inbound API |  |  |  | cannot
71 | Truemoney outbound API | [2305-08] Migrate trueMoney API | Development on going |  | need check spec
72 | Upticon inbound and outbound API |  |  |  | need check spec
73 | ACEmoney inbound API |  |  |  | need check spec
74 | RIA inbound API for C2C |  |  |  | need check spec
75 | Terrapay inbound API |  | Development on going |  | need check spec
76 | 9pay outboud and inbound API | [2306-19] 9Pay Outbound API |  |  | need check spec
77 | Sendmn inbound API |  |  |  | need check spec
78 | Pingpong Card Payment API |  |  |  | need check spec
79 | AYA bank API | [2207-22] Aya Bank API(Myanmar) | Development on going |  | need check spec
80 | Universal Bank | [2306-14] Universal Bank API Integration | Development on going |  | need check spec
81 | India direct partner API |  |  |  | need check spec
82 | JME inbound and outbound API |  |  |  | need check spec
83 | Online Handphone sales using GME app |  | Planning on going |  | cannot
84 | Explanation and guide to error messages |  | Planning on going |  | cannot
85 | Wallet topup using KFTC | [2304-15] Wallet Deposit using KFTC | Development on going | 2023-08-29 | can
86 | LY Hour Cash Payment for KHR Payout | [2304-05] KHR Cash Payment with Lyhour |  |  | Done
87 | Bangkok Bank API |  |  |  | need check spec
88 | TazaPay c2c API |  |  |  | need check spec
89 | B2B Paynoeer API |  |  |  | need check spec
90 | B2B Ebury API |  |  |  | need check spec
91 | B2B Partner 1 API |  |  |  | need check spec
92 | B2B Partner 2 API |  |  |  | need check spec
93 | B2B Partner 3 API |  |  |  | need check spec
94 | Tranglo API in New Architecture |  | publish done |  | Done
95 | Dutch Bangla API in new Architecture |  | Planning on going |  | need check spec
96 | Payform Inbound and Outbound API |  |  |  | need check spec
97 | Allow Customer to send money and put fixed deposit in their country. |  |  |  | cannot
98 | Airticket by powercall |  |  |  | cannot
99 | Multi currency wallet |  |  |  | cannot
|  | [2304-12] Add Japanese Language in Mobile | Publish done |  | Done
|  | [2306-04] Make receiver mobile prefix selectable | Publish done |  | Done