## Sheet1
Sn | IT Issue | Description | Remarks
1 | Saving the customer user id when logout | customer user id field is blank after logout, user id should be saved when customer logout . | 2020-01-28
2 | Easy Remit Customer: error in uploading id card | can not upload id card of Easy remit customer from Agent id | 2020-01-22
3 | Auto debit renew last page is blank | while renew and add auto debit from our core system at last page it is blank we should pop up successful message. | 2020-01-31
4 | Push Notification |  | 2020-02-07
5 | Online Registration error: Gender (other) city field(blank) | while registering customer from mobile app we received mistake gender and city field as blank. | 2020-01-23
6 | City field mandatory for agent id too | Make city filed should be mandatory while approving customer from agent id. | 2020-01-23
7 | Myanmar transaction error | Transaction failed message popup but transaction was successful. | 2020-01-22
8 | Sender Address (special character error) | block special character while registering customer. | 2020-01-21
9 | Double Country code | while editing customer details in customer mobile no fields country code added twice. | 2020-01-28
10 | Notify cs for unsuccessful transaction | Money deduction from customer bank account for failed transaction need to make new menu to notify cs . | 2020-01-29
11 | Missing Agent bank in branch list of ISLAMI bank | While sending money from new app some of the ISLAMI bank agent are missing in branch list. | 2020-01-23
12 | BKASH Problem from New App in android Mobile | Cant not send BKASH transaction from android app . | 2020-01-21
13 | Bangladesh DBBL bank validation problem | All detail are correct but still bank validation failed for DBBL bank deposit transaction | 2020-01-23
14 | Search By virtual Wallet number | Add customer wallet option while searching customer statement both in agent and admin id. | 2020-01-22
15 | Search By mobile no in Agent id | Add mobile no field in customer search option In Agent id . | 2020-01-23
16 | auto debit req block after 2 time failed | In new customer registration process block auto debit req to customer after 2 failed requested from customer. | Can not
17 | Thailand Transaction Synchronization problem |  | 2020-02-07
18 | Sri Lanka Transaction synchronization problem |  | Don't need

## Sheet2
Sn | IT Issue | Description | Remarks
1 | Saving the customer user id when logout | 고객이 로그아웃 후에 UserID가 저장되어서 입력하지 않고, 패스워드만 입력할 수 있도록 | 2020-01-28 | JB
2 | Easy Remit Customer: error in uploading id card | can not upload id card of Easy remit customer from Agent id | 2020-01-22 | Chris
3 | Auto debit renew last page is blank | while renew and add auto debit from our core system at last page it is blank we should pop up successful message. | 2020-01-31 | Max
4 | Push Notification |  | 2020-02-07 | Chris, James
5 | Online Registration error: Gender (other) city field(blank) | Agent메뉴에서 Online Customer > Customer Setup 에서 City, Gender필드가 비어있는 경우가 발생 미얀마에서는 Gender 필드가 'Other' 로 들어가 있음 | 2020-01-23 | Chris
6 | City field mandatory for agent id too | Agent메뉴에서 Online Customer > Customer Setup 에서 City 필드가 비어 있는 경우에 Approve가 되면 안된다. | 2020-01-23 | Chris
7 | Myanmar transaction error | 송금은 성공했으나, 고객에게는 실패 메시지가 나오는 경우 메시지: -Error occurred while sending Transaction, Please contact GME. -The request timed out | 2020-01-22 | Saroj
8 | Sender Address (special character error) | 회원가입에서 주소입력시에 알파벳만 입력 가능하도록 | 2020-01-21 | James
9 | Double Country code | 송금이 성공하고 난뒤에, 모바일번호에 국가번호가 추가되는 현상(몽골, 남아프리카) | 2020-01-28 | Chris
10 | Notify cs for unsuccessful transaction | KFTC자동출금이체 실행후에 송금(국내/해외)실패시에 가상계좌로 입금되는 리스트 메뉴 추가 Wallet No, Customer Name, Amount | 2020-01-29 | Chris
11 | Missing Agent bank in branch list of ISLAMI bank | Old App에서 Islami bank 선택시에 Branch Name Missing | 2020-01-23 | Saroj
12 | BKASH Problem from New App in android Mobile | Cant not send BKASH transaction from android app . | 2020-01-21 | Preyea
13 | Bangladesh DBBL bank validation problem | DBBL Bank - Bank deposit 에서 Account Validation Error : receiver name dosen't match, but all receiver detail are correct | 2020-01-23 | Manoj
14 | Search By virtual Wallet number | Online Customer - Customer Statement 에서 현재는 Id Number만 조회가능, Wallet No도 조회가능하도록 | 2020-01-22 | Justin
15 | Search By mobile no in Agent id | Online Customer - Customer Setup 에서 현재는 Mobile 이지만 ARC조회되고 있음, Mobile, ARC모두 가능하도록 | 2020-01-23 | Justin
16 | auto debit req block after 2 time failed | In new customer registration process block auto debit req to customer after 2 failed requested from customer.
17 | Thailand Transaction Synchronization problem | Kbank Transaction status check | 2020-02-07 | Manoj
18 | Sri Lanka Transaction synchronization problem | Commercial bank 이미 스케쥴러에서 Status 체크를 하고 있음