## Issue List
Corridor | IT problems/ support requests | PIC | Issue Raised On | Remark | Issue solved on | Days Since issue raised | Remarks
Indonesia | Error: CustFirstName field is required: Saroj will check with Natthinee from ria and get back on jan 28 | Saroj | 2021-01-07 | Not yet checked, saroj wil update on 28 jan. |  | 15 | Working with Ria to solve this issue,solved by jan 21
Indonesia | Error: Input XML is Invalid. Schema Messages: The 'CustState' element has an invalid value according to its data type. Resolved | Saroj | 2021-01-07 | For other new cases yet to come saroj will update manually upon email confirmation by subash sir. | 2021-01-21 | Solved
Indonesia | Error: No Transaction received. Saroj will check with Ria and inform on n14th | Saroj | 2021-01-07 | Enabling two partner from api routing partner creates this issue for same country | 2021-01-21 | Solved
Indonesia | Invalid BankID for Country To Value. Balance has refunded to your Wallet. Saroj will check with Ria and inform on n14th | Saroj | 2021-01-07 | BRI routing Code has been changed then. Should be issue until and unless change by ria onn their side. | 2021-01-21 | Solved
Indonesia | Path parameter "tranId" value must not be null. Saroj will check with Ria and inform on 14th | Saroj | 2021-01-07 | after New RIA Api is published it should resolved the issue for Ria. on jan 28 |  | 15
Indonesia | Your transaction is on HOLD. Please contact GME (Estimated earning points: 0)Saroj will check with Ria and inform on jan 28 | Saroj | 2021-01-07 | Not yet checked, saroj wil update on 28 jan. |  | 15
CIS | DT minimum 100KRW : Will be done on 21st Jan | Andrew, Dibya | 2021-01-07 | will solve on jan 25 |  | 15
CIS | Automatic Name Check from Admin: | Max | 2021-01-07 | will solve on jan 29 |  | 15 | Max will check and inform on jan 21st
CIS | Branch address link in the app | Max | 2021-01-07 | will solve on jan 25 |  | 15 | MAX will give the publishing date on 21st Jan.
Vietnam | USD bank deposit TNX has not been available: will update status on 14th Jan by rajesh | Rajesh | 2021-01-07 |  | 2021-01-20 | Solved | Usd payout issue and Get Order status will solved on 15th Jan.
Vietnam | New banklist has not available: Saroj will update | Saroj | 2021-01-07 | will solve on jan 21 |  | Solved
Vietnam | Need to route Sacom bank txn to Exim/Donga API( becacuse Sacom bank service is not as good as Exim and Donga): Q2 | Saroj | 2021-01-07 | Not in priority currently |  | Solved
Vietnam | Install 'get-order-details' functions to get error messages in error ticket for team to monitor and route: Saroj will update on 14th Jan | Saroj | 2021-01-07 | will solve on jan 28 |  | Solved | Saroj will check and infom on 21st Jan.
Africa | Going Live for TerraPay Services/Countries: need to change agreement to terrapay UK, End of Feb will be done | Max | 2021-01-07 |  |  | 15 | Agreement is done, will go live on 18th of Feb
Bangladesh | Delay to receive transactios details mail : Dana will check and report to max by 8th Jan | Dana | 2021-01-07 |  |  | 15 | Max will provide the update on 21st Jan
Thailand | Please provide smart deposite guideline as Gmoneytrans: Q1 | Rajesh | 2021-01-07 | By the end of Jan provide file to max (15 language) |  | 15 | Q2
Bangladesh | Double payment of Agrani Bank and Bkash Txn, Txn paid in Bangladesh and sender also got refund in Korea: Manoj will update on 14th Jan | Saroj/manoj | 2021-01-07 | saroj will update on 1st of FEB |  | 15 | Waiting Api Document from agrani bank
Myanmar | AYA Bank Real Time Transfer (New Api) | Max | 2021-01-14 |  |  | 8 | Plan to go live for 4th of march
Vietnam | landing permission page to be In local languages, | Rey | 2021-01-14 | Rey will check the transation file and provide to MAX by jan28 |  | 8 | Max will send transalation file tomorrow
Sri lanka | start business with people's bank | Max | 2021-01-14 |  |  | 8 | Plan to go live on 28th jan
CIS | Receiver information modify page is loading until 3 to 4 sec everytime | Andrew, Dibya | 2021-01-14 | will solve on jan 25. |  | 8 | Max will check and inform on jan 21st
kenya | Mobile wallet: can not save rec details without middle name IOS | Manoj | 2021-01-14 | will solve on jan 25. | 2021-01-15 | Solved | Rajesh will check and inform on 21st jan
Africa | Gme control number was not showing on IOS app(receipt ) | Manoj | 2021-01-14 | will solve on jan 25. |  | 8 | already implemented in app will avaiable on next publish
Africa | Sender address(south korea) was not shown in receipt page | Manoj | 2021-01-14 | will solve on jan 25. |  | 8 | already implemented in app will avaiable on next publish
Gimhae | Customer can edit customer details after successful registration befor penny test verification both android & Ios | Andrew, Dibya,Preyea | 2021-01-21 | should by Feb 3rd
Cis | java script login error, | Andrew,Preyea | 2021-01-21 | Should by Feb 3rd
Myanmar | wrong myanmar font at unicode both in Ios | Rey | 2021-01-21 | Rey will coordinate and provide the correct file to max on jan 28
Philippines | No smart deposit option for I phone x max | max | 2021-01-21 | will solved on jan 25
Philippines | International top-up error plus option for utility bills | rajesh | 2021-01-21
Thailand | Counter cash deposit for IOS |  | 2021-01-21 | will solve on jan 25.
Bangladesh | while adding beneficiary details it shows bank Validation Failed for Dutch bangla bank | saroj | 2021-01-21 | will solve on jan 25.
Africa | change default currency rate value to 100000 krw for all mobile wallet | Max | 2021-01-21 | will solve on Feb 3rd
Vietnam | Iphone 5 can not install GME app (iOS 11 not supported) | Dibya | 2021-01-21 | will check with dibya and get back on jan 28
Indonesia | Status syncronization for ria | Max | 2021-01-21 | will solve by jan 25
indonesia | Memo field in customers profile where customer profile is displayed( verifu pending, approve pending, approved list, audit customer list, unapproved custoner list, modify customer list) | Manoj | 2021-01-21 | will solve on feb 11
Nepal | Customer can not login with both user id and email id | Max | 2021-01-21 | will solve by jan 25
Bangladesh | Branch agent update for all bangladesh partner (Dutch Bangla, Islami, Agrani) | Manoj | 2021-01-21 | will solve on jan 25.
Indonesia | Send password in sms after successfull registration from admin menu | Manoj | 2021-01-21 | manoj will solve on jan 25.
Formulas:
Days Since issue raised = IF([Issue solved on]>0,"Solved",TODAY()-[Issue Raised On])
Days Since issue raised = IF([Remark]>0,"Solved",TODAY()-[Issue Raised On])

## Sheet1
1 |  | 2 | 3 | Bangladesh
3 | Vietnam