## Sheet1
2021-02-01
How to Achieve 230k Txn By Dec 2021
Country | Type of Issue | No | Current Difficulty and Issues | Solution | By Whom | By When
General Issues | IT Operational | 1 | IT takes time to solve the problem of Korean local bank issues | Job specify based on local partner to Korean Engineer directly | Max | 2021-02-09
|  | 2 | IT support during lunch hour is to be continuously by 2 shifts | Separate 2 teams , 1 team goto lunch at 12 pm and another go at 1 pm | Subash | 2021-02-09
|  | 3 | Korean IT team is not available in weekend | 1 Korean Engineer to be available both on Weekends and holidays on rotation
|  | 4 | IT Support during night time should be faster | Give view access o flive Server to Nepal Support Engineer for troubleshooting | Max
|  | 5 | Voucher not generated in time, dut to load in server | Separate the Data Yearwise and store separately | Max | 2021-02-28
| IT Development | 6 | Slow development by IT
|  | 7 | Many bugs when new feature is added | Any new publish affecting to cusstomers should also be approved by Marketing, Operations and Recon | Max
| Mobile App | 8 | Error message; Email Notice, SMS, Push notification, Txn Status, by multi language( E-9 pay,Coinshot have it) | Start By translating Txn Status in Local language | Subash | 2021-02-24
|  | 9 | Need guideline on how to use the features in the mobile app | Start by providing guideline on how to use Smart Deposit | Subash | 2021-02-09
|  | 10 | App is not Vietnamese friendly, need to translate everything in the app to Vietnamese language | Start by providing guideline on how to use Smart Deposit in all 15 languages | Subash | 2021-02-24
|  | 11 | Don’t make customer update their app frequently | Publishing once a month: Last Wednesday of every month. Allow use even if customers don’t update | Max | 2021-02-24
|  | 12 | in-app banner for marketing promomtions corridorwise | To make and admin menu to upload poster by country wise, so that customers can see according to their registered country | Max | 2021-03-31
| Marketing | 13 | GME News in newspapers , How to do plan to be presented ? |  | Clarisa | 15th Feb
|  | 14 | As a whole company promotion campaign big Scale, What promotion can be done that can fit to all 15 corridors? |  | Diyorbek | 15th Feb
|  | 15 | Need to Make good quality corporate video , Sundariya will give a basic concept of the video |  | Sundariya | 15th Feb
Cambodia |  | 14 | For on hold txn, after we release the txn we should send push notification in Local language
Indonesia |  |  | 3. Payout problem by BNI ------------------------------->Will tie up with BRI
|  |  | Send email to BNI to recruit one staff for GME's support to provide weekend support |  | Clarisa
Mongolia |  |  | Recruit 3 staffs on probation |  | Sundariya
Thailand |  |  | Payout partner problem with Tranglo, find new partner
Bangladesh
Vietnam |  |  | 1. Pre funding problem--> Still problem
|  |  | 2.Should sell in cheap price-> Rey to propose the cost and target txn |  | Rey | 15th Feb