## Sheet1
Corridor | IT problems/ support requests | PIC | Issue Raised On | Days Since issue raised | Issue solved on | Remark
CIS | Automatic Name Check from Admin: | Summer | 2021-01-07 | 46 |  | Diyorbek will test together with pheakthra on 18 Feb.
Vietnam | Install 'get-order-details' functions to get error messages in error ticket for team to monitor and route: Saroj will update on 14th Jan | Saroj | 2021-01-07 | Solved |  | Rajesh will Test with Saroj test and provide feedback on Feb 18.
Africa | Going Live for TerraPay Services/Countries: need to change agreement to terrapay UK, End of Feb will be done | Subash | 2021-01-07 | 46 |  | Go-live by Feb 22.
Thailand | Please provide smart deposit guideline as Gmoneytrans: Q1 | Rajesh | 2021-01-07 | 46 |  | Will publish by March 31.
Bangladesh | Double payment of Agrani Bank and Bkash Txn, Txn paid in Bangladesh and sender also got refund in Korea: Manoj will update on 14th Jan | Saroj/manoj | 2021-01-07 | 46 |  | Api Published in Live Production, Live testing will be done by rajesh & sajib on Feb 18.
Myanmar | AYA Bank Real Time Transfer (New Api) | Subash | 2021-01-14 | 39 |  | Agreement is Pending from AYA Bank side.
Vietnam | landing permission page to be In local languages, | Rey | 2021-01-14 | 39 |  | will publish in Android Feb 24.
Sri lanka | start business with people's bank | Max | 2021-01-14 | 39 |  | Will go live on Feb 18.
Africa | Sender address(south korea) was not shown in receipt page | Max | 2021-01-14 | 39 |  | already implemented update after Android app publish on Feb 24
Gimhae | Customer can edit customer details after successful registration befor penny test verification both android & Ios | Rajesh | 2021-01-21 | 32 |  | rajesh will check and verify on Feb 19
CIS | java script login error, | Andrew,Preyea | 2021-01-21 | 32 |  | Max will remind Andrew and update on Feb 19.
Myanmar | wrong myanmar font at unicode both in Ios | Andrew Dibya | 2021-01-21 | 32 |  | Metting with Andrew, clarisa, Rey, Nini & Pim on Feb 18 at 4:30 pm.
Africa | change default currency rate value to 100000 krw for african countries with mobile wallet | max | 2021-01-21 | Solved | . | Halima already provided the list of the country and payout service(order wise) by March 31.
Indonesia | Status syncronization for ria | Max | 2021-01-21 | 32 |  | will solve on Feb 18.
indonesia | Memo field in customers profile where customer profile is displayed( verify pending, approve pending, approved list, audit customer list, unapproved custoner list, modify customer list) | Manoj | 2021-01-21 | 32 |  | Published on Testing, New feedback received, will complete by 25 Feb
Bangladesh | Bkash transaction : if customer have single name transaction can not proceed ( but name validation is success) | Saroj | 2021-01-28 | 25 |  | Saroj will verify in Live Test in new Api on Feb 19.
Cambodia | ACLEDA bank ddposit real time with Wing Never update status to Paid | Saroj | 2021-01-28 | 25 |  | Saroj will complete by Feb 24.
Thailand | Wallet number copy function in the app, just like Coinshot | Subash | 2021-02-04 | 18 |  | Provided the design to the app team, will Publish on March 31.
Thailand | User that have IBK that opened by passport cannot deposit money to wallet | Manoj | 2021-02-04 | 18 |  | Pimporn will provide the list of those customer on Feb 18 & Max will check with IBK and update on Feb 25.
Thailand | Beneficiary name with dot (.) cannot send money though Tranglo | Saroj | 2021-02-04 | 18 |  | Will solve for removing dots(Mr. Miss. ) by Feb 25.
Bangladesh | Translation for auto debit expiry | Sajib | 2021-02-04 | 18 |  | Sajib will fine tune the design and provide to Max on Feb 18.
Mongolia | Download PDF receipt for inbound txn (for immigration use) | Diyorbek | 2021-02-04 | 18 |  | Will Publish on March 31.
Mongolia | Inbound txn Customer Statement (receiver) | sundariya | 2021-02-04 | 18
Mongolia | Remaining Inbound txn Limit in USD have to show in app | Diyorbek | 2021-02-04 | 18 |  | Will Publish on March 31.
Africa | Payout amount/rate issue in slab Ghana Kenya and Uganda | Saroj | 2021-02-04 | 18 |  | Rajesh will check with saroj on Feb 23.
Africa | South Africa Currency Issue. | Saroj | 2021-02-05 | 17 |  | Rajesh will check with saroj on Feb 23.
Africa | Change the positions to Mobile Wallet, Bank Deposit, Cash Payment UGANDA GHANA KENYA ZAMBIA RWANDA | Saroj | 2021-02-06 | Solved | 2021-02-19 | Done
Africa | Change the position of Cash Payment, Bank Deposit for MOROCCO | Saroj | 2021-02-18 | Solved | 2021-02-19 | Done
China | Change the positions of bank deposit and mobile wallet | Saroj | 2021-02-04 | Requested
CIS | Admin Account Statement needs to show co.number for DT, International and Domestic TOPUP (E.g. DT-Wallet Deposit - 202102083832728372) | Max | 2021-02-08 |  |  | will publish by Feb 25.
Cambodia | Account name verification to be available from double documents, passport & ARC, and be able to use 2 bank account through autodebit and verification being automatic |  | 2021-02-08 | Q2
Vietnam | Change Default Amount to KRW 1,000,000 |  | 2021-02-08 |  |  | Will Publish on Android by Feb 24.
Vietnam | When clicking on GME notification, the notice will be shown directly. |  |  | Q1
Cis | Change Contact control number in GME system to Contact control (make transaction Real time) | Saroj | 2021-02-18
Africa | Send message after successful registration as you can send 1st transaction with zero service charge |  | 2021-02-18