## Priority for July 2022
Priority list for July, 2022
SN | Tasks | Type | Deatails | Remarks
1 | New Wallet number Assign From system for KJ push failed customer | New Development |  | [2207-05] Customer detail not pushed to KJ Bank
2 | Find ID/Password function in login menu | New Development |  | [2206-10] ID, Password Finding
3 | Channeltalk divert customer according to language or nationality | New Development
4 | Notification/Notice (Onesignal) | New Development | Use Third party app Onesignal for Push notification | Setup segment necessary, deeplink, trigger [2205-34] Push Notification using OneSignal
5 | Send Bulk SMS in native language
6 | Branch menu in login page | New Development |  | [2207-10] Branch Menu in Login Page
7 | KFTC self verification | New Development |  | [2207-01] KFTC Self Certification
8 | Autodebit issue for NH Bank | issue
9 | Countrywise promotion banner in app as webview | New Development | All details will be displayed in website
10 | New Transaction History in Mobile App | New Development |  | Memo field should be added in (local transfer) transactio report [2112-01] New History in Mobile App
11 | Bkash and Rocket separately instead of mobile wallet | New Development | 방글라데시(Bank,Mobile,Cash) => Bank,Cash, Bkcash, Rocket로 변경
12 | show ex rate with Service charge fee included and excluded (dynamic) | New Development | 오늘의 환율화면에서 송금수수료 포함여부를 관리자페이지에서 지정
13 | All payout partner for cash pickup for CIS | New Development | 체크
14 | Homepage renew | New Development
15 | Fix app crash: OCR camera | issue |  | [2207-15] OCR Camera Issue
16 | Show the Payout amount without Service Charge | New Development | 오늘의 환율화면에서 송금수수료 포함여부를 관리자페이지에서 지정
17 | Create 2 Popup pages in Mobile app which can be configurable by country wise, Receiving Country Wise, Partnerwise etc | New Development | One page Should be after login and 1 page should be after successfully send txn | place to display the pop-up message, will be used as a trigger in onesignal
18 | Change default amount for Exchange rate calculation from Core system | New Development | 8월 16일 배포예정 | [2205-33] Change default Amount for Exchange rate calculation from Core system
19 | Setup Service Charge and Pay Commission for USD txn in Core system | New Development |  | [2205-26] Setup Service Charge and Pay Commission in Core
20 | Pay commission calculation base on payout amount | New Development | 송금금액별 수수료를 변경가능하게 설정 | [2205-28] Pay commission calculation base on payout amount
21 | Remove Logic to cancel principal amount for Wing transaction | issue |  | [2207-06] Remove Logic to cancel principal amount for Wing transaction
22 | New Registration Process | New Development
23 | QR ticketing function in Mobile App | New Development | allow customer to buy ticket for different event organized by their corridor.
24 | Customize Admin User Role as per Corridor for Transaction reports | New Development |  | [2207-07] Customize Admin User Role as per Corridor for Transaction reports
25 | Ria B2B Inbound/outbound | API development
26 | App Hyperlink | New Development

## Sheet1
SN | Tasks | Type | Deatails | Remarks
1 | Zero Pay | New Development |  |  | publish
2 | ATM Withdraw UI/UX | New Development |  |  | done, but no publish
3 | Schedule Payment | New Development |  |  | hold
4 | New Transaction History in Mobile App | New Development
5 | Request Customers Missing ID Card Picture in the Mobile app | New Development | If Customer ID card picture missing, then Admin system request for ID card uploading then the ID card field should pop up in Customer app side
6 | Voice Phishing -Hi Korea | New Development
7 | Inbound/Outbound Logic | New Development | Make a new table to put the accumulated sending amount after every Txn--> Assign to saroj ASAP
8 | KT Sim card top up from Mobile | New Development
9 | Password Validator | New Development
10 | Add Real-Name Module in Overseas Remittance | New Development
11 | Add hyper link between the mobile app pages | New Development
12 | Customer ID Card Managmenet | New Development | Save all the ID Card images received from Customers
13 | Setup Service Charge and Pay Commission for USD txn in Core system | New Development
14 | Kicc Virtual wallet | New Development
15 | Pay commission calculation base on payout amount | New Development
16 | Adding new parameter field in Mobile app | New Development
17 | Uzcard Api | New Development
18 | Alif Api | New Development
19 | Sim Paisa Api | New Development
20 | New Wallet number Assign From system for KJ push failed customer | New Development
21 | Autodebit not shown after successful registration | issue
22 | Change default amount for Exchange rate calculation from Core system | New Development |  | Android not started, iOS and core finished
23 | Notification/Notice |  | Use Third party app Onesignal for Push notification | Setup segment necessary, deeplink, trigger
24 | Autodebit issue for NH Bank | issue
25 | Show the Payout amount without Service Charge- Sajib,Jagath
26 | Create 2 Popup pages in Mobile app which can be configurable by country wise, Receiving Country Wise, Partnerwise etc |  | One page Should be after login and 1 page should be after successfully send txn | place to display the pop-up message, will be used as a trigger in onesignal
27 | Remove Logic to cancel principal amount for Wing transaction | issue
28 | Memo field should be added in (local transfer) transaction receipt | New Development
29 | Find ID/ Password function in login menu in mobile app | New Development
30 | Development for Mobile wallet/Bill payment function |  | Use bkash and rocket separately instead of mobile wallet.
31 | Show limit and payout time while calculating ex rate before sending transaction |  |  | website
32 | Countrywise banner (promotions) to be displayed in webview |  |  | website
32 | QR ticketing function in Mobile App |  | allow customer to buy ticket for different event organized by their corridor.
32 | Zalo API
32 | Customize Admin User Role as per Corridor for Transaction reports | New Development
32 | Ria B2B Inbound/outbound | API development
32 | Channeltalk divert customer according to language
33 | Homepage renew
34 | Branch menu in login page
35 | App Hyperlink
36 | KFTC verification

## Sheet2
Hwaseong | Celia | ec | Monthly limit per each card: 500/500k per month
Gimhae | Jib
Gwangju | Pisey
Ansan | Anu
Suwon | Sophie
CIS | Akmaljon
MT | Uuree
Daerim | Hedy
Songuri | Lovely
DDM | Amrita

## Sheet3
| Issue | By who | Time necessary | By When
1 | Bkash and Rocket separately instead of mobile wallet | Saroj | 1 week development 2 days testing Total: 9 days
2 | Show ex rate with Service charge fee included and excluded (dynamic) | Saroj | Total : 7 days
3 | Display All cash pickup payout partners for CIS | Saroj