## Sheet1
Task Priority
Fix existing issues, Bugs ,double refund cases
New Developments
New Partner API

## Sheet2
1 | Cashbee
Cashbee Auto Recharge
Cashbee Notification
Cashbee iOS
2 | KFTC | [7 empty] | Zeropay?
|  | KFTC Self Certification with Gmoney method | [6 empty] | Bill payment?
|  | KFTC Self Certification with Coinshot method | [6 empty] | Show all limit?
3 | Receiver Initiated Inbound
|  | Receiver Initiated Inbound Vietnam | [6 empty] | Alipay QR code
Receiver Initiated Inbound Mongolia
4 | Register GME on Zalo
Easy remit customer registration via Zalo
1) OCR + Face recognition via Comtrue
5 | Homepage renewal
New homepage design
6 | Hyperlink inside add
If no balance in wallet --> ask to register autodebit
7 | New registration process (easy + normal)
| Corridor | IT problems/ support requests | PIC | Issue Raised On | Days Since issue raised | Target to be solved on | Issue solved on | Remark
|  | No of It Issues |  | 18
1 | General | Show limit and payout time while calculating ex rate before sending transaction (In case of customer reached monthly or daily limits, app should show balance of montly /daily limits for all users in the error's popup msg and guide of when can they start to transfer again both local transfer and oversae transfer) | Manoj | 2022-04-28 | 343 | 2023-03-28 |  | Cancelled and need to restart the project 2023-02-02: Waiting for the confirmation for compliance team
2 | General | NH Auto debit issue for some customers | Boren |  | Waiting for boren |  |  | Waiting for boren to send us some cases (First complaint date: 2022-08-02)
3 | General | Group report is not working properly- data is not accurate (transaction and registration) | Manoj | 2022-12-01 | 126 | 2023-02-14 |  | 2023-02-02: To-be tested after publish 2023-04-03: Planning to Published
4 | General | Registration report - 1st transaction data is not accurate |  | 2022-12-01 | 126 | 2023-02-14 |  | 2023-02-02: To-be tested after publish 2023-04-03: Planning to Published
5 | Cambodia | In bank deposit menu, if customer select wing bank, route transactions to Wing wallet (partner wing - wallet deposit) | Boren | 2022-12-29 | Cancelled by Boren |  | 2023-03-02
6 | Myanmar | Payment method translation is wrong in mobile | Manoj | 1/12/2023 | Solved |  | 2023-01-26
7 | General | While exporting reports to excel, it should export all results from DB. not only 1000 which shows in the front page | Sagar | 2023-02-22 | 43 | 2023-03-30 |  | (2023-01-26)) There are too many report menus. We need to decide the report menu. When the report menu is decided, the development will begin. Issue Raised Date should be the date after decide report menu. [Menu] Remittance>>report master>>Transaction Report master Remittance>>reports>>Transaction/Registration Reports Remittance>>reports>>native country wise txn report Remittance>>reports>>Transaction/Registration group Report [2302-15] Export Report to Excel
8 | General | Add API logs for all partners in API log table in core system (start with ria) KoronaPay Thunes TerraPay BNI BOP Tranglo | Subash | 2023-01-12 | 84 | 2023-02-28 |  | Project created [2302-03] Add Missing API logs in Core
9 | General | User should not be logged out if there is any network issue from user's side or gme side | Dhan | 2023-01-19 | 77 | 2023-02-28 |  | Santosh is researching on it [2302-05] Change Logging Out Rule of Mobile App
10 | Cambodia | Consider bank deposit transactions as paid after successfully posted | Pujan | 2023-01-26 | 70 | 2023-02-26 |  | [2302-08] Change Payment Status on Cambodia Txn 2023-03-09: Development completed. will be published togather with realname issue fixing
11 | Cambodia | Wing: when partner cancel cash deposit transaction, it should be cancelled automatically in GME. Need to check API. If dont't have call back api, cancel the project | Boren |  |  |  |  | Waiting for boren to send us API document
12 | General | Customer doesn't receive emails after reset password and find user ID | Dhan | 2023-02-02 | Solved | 2023-03-02 | 2023-04-03 | [2302-10] Change Email Module 2023-04-03: Published
13 | General | Used store coupons availble in the "available" tab in mobile - New history - coupon | Manoj | 2023-02-02 | 63 | 2023-03-02 |  | feedback project
14 | General | Store deposit: Even when the existing request passes 10 mins, user cannot request for new deposit request.. | Nepal Subash |  | Removed as there are no any new cases |  |  | Case reported: 2023-02-09 IT tried to recreate it, but it is not being recreated. If this phenomenon is found, please show the video.
15 | Cambodia | Automatic email request to wing partner if cancel request from mobile and Core system. | Rajesh
16 | General | Show only available payment method in today's rate for correnspondant currency | Max | 2023-03-09 | 28
17 | General | In today's menu, default currency should be setup from core system | Max | 2023-03-09 | 28
19 | General | Add control number filter in Local topup search menu | Sagar | 2023-03-23 | 14
20 |  | Add Column in approve holded txn menu |  | 2023-03-30 | 7
21 |  | Seperate GIBL deposit transaction report in Report ->vReport master |  | 2023-03-30 | 7
22 |  | iOS: When open app for the first time, default language is Myanmar language. (it should be English) | Manish | 2023-03-30 | 7
23 |  | iOS: Russian language doesn't work before login to app |  | 2023-03-30 | 7
24 |  | Android: Cashbeee balance is different in (monthly recharge-use) and actual balance |  | 2023-03-30 | 7
25 |  | Koronapay Inbound issue
Formulas:
Days Since issue raised = IF([Issue solved on]>0,"Solved",TODAY()-[Issue Raised On])

## IT Issue List
| Corridor | IT problems/ support requests | PIC | Issue Raised On | Days Since issue raised | Target to be solved on | Issue solved on | Remark
|  | No of It Issues |  | 18
1 | General | Show limit and payout time while calculating ex rate before sending transaction (In case of customer reached monthly or daily limits, app should show balance of montly /daily limits for all users in the error's popup msg and guide of when can they start to transfer again both local transfer and oversae transfer) | Manoj | 2022-04-28 | 343 | 2023-03-28 |  | Cancelled and need to restart the project 2023-02-02: Waiting for the confirmation for compliance team
2 | General | NH Auto debit issue for some customers | Boren |  | Waiting for boren |  |  | Waiting for boren to send us some cases (First complaint date: 2022-08-02)
3 | General | Group report is not working properly- data is not accurate (transaction and registration) | Manoj | 2022-12-01 | 126 | 2023-02-14 |  | 2023-02-02: To-be tested after publish 2023-04-03: Planning to Published
4 | General | Registration report - 1st transaction data is not accurate |  | 2022-12-01 | 126 | 2023-02-14 |  | 2023-02-02: To-be tested after publish 2023-04-03: Planning to Published
5 | Cambodia | In bank deposit menu, if customer select wing bank, route transactions to Wing wallet (partner wing - wallet deposit) | Boren | 2022-12-29 | Cancelled by Boren |  | 2023-03-02
6 | Myanmar | Payment method translation is wrong in mobile | Manoj | 1/12/2023 | Solved |  | 2023-01-26
7 | General | While exporting reports to excel, it should export all results from DB. not only 1000 which shows in the front page | Sagar | 2023-02-22 | 43 | 2023-03-30 |  | (2023-01-26)) There are too many report menus. We need to decide the report menu. When the report menu is decided, the development will begin. Issue Raised Date should be the date after decide report menu. [Menu] Remittance>>report master>>Transaction Report master Remittance>>reports>>Transaction/Registration Reports Remittance>>reports>>native country wise txn report Remittance>>reports>>Transaction/Registration group Report [2302-15] Export Report to Excel
8 | General | Add API logs for all partners in API log table in core system (start with ria) KoronaPay Thunes TerraPay BNI BOP Tranglo | Subash | 2023-01-12 | 84 | 2023-02-28 |  | Project created [2302-03] Add Missing API logs in Core
9 | General | User should not be logged out if there is any network issue from user's side or gme side | Dhan | 2023-01-19 | 77 | 2023-02-28 |  | Santosh is researching on it [2302-05] Change Logging Out Rule of Mobile App
10 | Cambodia | Consider bank deposit transactions as paid after successfully posted | Pujan | 2023-01-26 | 70 | 2023-02-26 |  | [2302-08] Change Payment Status on Cambodia Txn 2023-03-09: Development completed. will be published togather with realname issue fixing
11 | Cambodia | Wing: when partner cancel cash deposit transaction, it should be cancelled automatically in GME. Need to check API. If dont't have call back api, cancel the project | Boren |  |  |  |  | Waiting for boren to send us API document
12 | General | Customer doesn't receive emails after reset password and find user ID | Dhan | 2023-02-02 | Solved | 2023-03-02 | 2023-04-03 | [2302-10] Change Email Module 2023-04-03: Published
13 | General | Used store coupons availble in the "available" tab in mobile - New history - coupon | Manoj | 2023-02-02 | 63 | 2023-03-02 |  | feedback project
14 | General | Store deposit: Even when the existing request passes 10 mins, user cannot request for new deposit request.. | Nepal Subash |  | Removed as there are no any new cases |  |  | Case reported: 2023-02-09 IT tried to recreate it, but it is not being recreated. If this phenomenon is found, please show the video.
15 | Cambodia | Automatic email request to wing partner if cancel request from mobile and Core system. | Rajesh
16 | General | Show only available payment method in today's rate for correnspondant currency | Max | 2023-03-09 | 28
17 | General | In today's menu, default currency should be setup from core system | Max | 2023-03-09 | 28
19 | General | Add control number filter in Local topup search menu | Sagar | 2023-03-23 | 14
20 |  | Add Column in approve holded txn menu |  | 2023-03-30 | 7
21 |  | Seperate GIBL deposit transaction report in Report ->vReport master |  | 2023-03-30 | 7
22 |  | iOS: When open app for the first time, default language is Myanmar language. (it should be English) | Manish | 2023-03-30 | 7
23 |  | iOS: Russian language doesn't work before login to app |  | 2023-03-30 | 7
24 |  | Android: Cashbeee balance is different in (monthly recharge-use) and actual balance |  | 2023-03-30 | 7
25 |  | Koronapay Inbound issue
Formulas:
Days Since issue raised = IF([Issue solved on]>0,"Solved",TODAY()-[Issue Raised On])

## 2023.03.23
IT Development Priority List 2023 Q2&Q3 |  | Feedback project
SN | Tasks | Gme project name |  | IT Target | Make Schedule | Tentative Start Date | Tentative Publish Date
1 | Cashbee Auto Recharge | [2303-03] Cashbee Card using GME Pay v2.0 | Stag Testing | 2023-03-07' | can
2 | Cashbee Notification: When customer use subway notification should be sent to GMEapp | We need to make V2.1 |  | 2023-04-13 | can
3 | Zero Pay | [2110-18] Zeropay in Mobile App | Stag testing finished |  | can
4 | Bill Payment | [2209-16] Bill Payment using Sampath Bank [2301-12] Bill Payment History(Mobile, Core) | Developer testing ongoing |  | can
5 | KFTC Self Certification with Gmoney method | [2207-01]KFTC Self Certification | Development finished. Testing not done |  | can
6 | KFTC Self Certification with Coinshot method | We need to make V2.0 |  |  | can
7 | Fix the Easypromos issues: second name Null issue; point now shown in app, even though customer won the point | Feedback project | Assigned to Subash but not finished yet | 2023-04-07 | can
8 | Receiver Initiated Inbound Vietnam | [2301-08] New Type Inbound Service | Development on going |  | can
9 | Receiver Initiated Inbound Mongolia | We need to make V2.0 |  |  | can
10 | GME Check Card |  |  |  | cannot
11 | Easy remit customer registration via Zalo (OCR + Face recognition via Comtrue) |  |  |  | cannot
12 | Divert customers to corresponding CS according the chosen language |  |  |  | cannot
13 | Hyperlink inside app (If no balance in wallet --> ask to register autodebit) |  |  |  | cannot
14 | Group report is not working properly- data is not accurate (transaction and registration) | Feedback project | publish done |  | can
15 | Add beneficiary using QR-Alipay |  |  |  | cannot
16 | Octa Solution implementation | [2207-11] Setup AML Solution | we need check with partner |  | can
17 | Macro Recon for partner and Bank Recon |  |  |  | cannot
18 | New Homepage design | [2204-02] Change Main Page in Mobile App | we need make schedule |  | can
19 | Register customer device; if detect device change, ask for more questions (DOB, choose receiver and etc) |  |  |  | cannot
20 | Remove OTP (replace OTP with simple PW) |  |  |  | cannot
21 | Merchants Platform for B2B |  |  |  | cannot
22 | New Core Admin System for B2B |  |  |  | cannot
23 | Registration report - 1st transaction data is not accurate | Feedback project | publish done |  | can
24 | Koronapay Inbound issue | [2302-11] Fix Inbound Issue in Korona | we need make schedule |  | can
25 | In bank deposit menu, if customer select wing bank, route transactions to Wing wallet (partner wing - wallet deposit) | Project not created | SP Change : 2h |  | can
26 | Payment method translation is wrong in mobile | Feedback project |  |  | can
27 | While exporting reports to excel, it should export all results from DB. not only 1000 which shows in the front page | [2302-15] Export Report to Excel |  |  | can
28 | Add API logs for all partners in API log table in core system (start with ria) KoronaPay Thunes TerraPay BNI BOP Tranglo | [2302-03] Add Missing API logs in Core |  |  | can
29 | User should not be logged out if there is any network issue from user's side or gme side | [2302-05] Change Logging Out Rule of Mobile App |  |  | can
30 | Consider bank deposit transactions as paid after successfully posted | [2302-08] Change Payment Status on Cambodia Txn |  |  | can
31 | Wing: when partner cancel cash deposit transaction, it should be cancelled automatically in GME. Need to check API. If dont't have call back api, cancel the project | [2302-16] Cancel Wing Cash-Payment with Callback |  |  | can
32 | Customer doesn't receive emails after reset password and find user ID | [2302-10] Change Email Module |  |  | can
33 | Cancellation Email to partner via API ( Borens requirement) | Project not created |  |  | can
34 | Used store coupons availble in the "available" tab in mobile - New history - coupon | Feedback project |  |  | can
35 | Store deposit: Even when the existing request passes 10 mins, user cannot request for new deposit request.. | [2209-05] Show All Limit in Mobile App |  |  | can
36 | Automatic email request to wing partner if cancel request from mobile and Core system. | Project not created |  |  | can
37 | Show only available payment method in today's rate for correnspondant currency |  |  |  | cannot
38 | In today's menu, default currency should be setup from core system |  |  |  | cannot
39 | Add control number filter in Local topup search menu | [2303-13] Bug fixing in Domestic topup search menu |  |  | can
40 | Add Column in approve holded txn menu | Project not created |  |  | can
41 | Separate GIBL deposit transaction report in Report ->Report master | Project not created |  |  | can
42 | iOS: When open app for the first time, default language is Myanmar language. (it should be English) | Feedback project |  |  | can
43 | iOS: Russian language doesn't work before login to app | Feedback project |  |  | can
44 | Android: Cashbeee balance is different in (monthly recharge-use) and actual balance | Feedback project |  |  | can
45 | Cashbee iOS |  |  |  | cannot
46 | New registration process (easy + normal) |  |  |  | cannot
47 | Show Revenue wise report to Marketing heads based on their country only |  |  |  | cannot
48 | Send Bulk SMS in native language |  |  |  | cannot
49 | Kakaotalk integration for informing txn status (copy Sentbe) |  |  |  | cannot
50 | Service Charge and Pay commission Based on Multiple payout currency (dynamic service charge setup) | [2205-26] Setup Service Charge and Pay Commission in Core |  |  | can
51 | Pay commission calculation based on payout amount (dynamic pay commission setup) | [2205-28] Pay commission calculation base on payout amount |  |  | can
52 | Create 2 Popup pages in Mobile app which can be configurable by country wise, Receiving Country Wise, Partnerwise etc |  |  |  | cannot
53 | QR ticketing function in Mobile App |  |  |  | cannot
54 | Using Hi Korea for auto approval of new customers |  |  |  | cannot
55 | Make a New table to calculate the Annual limit for USD 50,000 for both Inbound/Outbound | [2210-13] Change Inbound/Outbound 50000 USD Limit Checking |  |  | can
56 | Payout time while calculating ex rate before sending transaction | [2209-05] Show All Limit in Mobile App |  |  | can
57 | Show the txn limit (1-time limit, 1-day limit, Yearly limit( while calculating ex rate) | [2209-05] Show All Limit in Mobile App |  |  | can
58 | Allow Schedule payment adding from Core system by GME Staff | [2111-08] Schedule Payment |  |  | can
59 | Create special coupon for particular bank account (charity) |  |  |  | cannot
60 | Auto checking phone carrier for both internation and domestic phon top up | Feedback project |  |  | can
61 | Sendmn QRPay integration | No project |  |  | cannot
62 | IME QRPay integration | [2208-18] Global QR Payment with IMEPay |  |  | cannot
63 | KakaoPay QR integration | No project |  |  | cannot
64 | Allow to add beneficiary using QR Code to Send Money e.g. Alipay Beneficiary QR |  |  |  | cannot
65 | Wechat API | [2210-26] WeChat Wallet Service for China |  |  | cannot
66 | Smartswift API | [2210-02] Smart-Swif33 Inbound API |  |  | can
67 | Ipay remit inbound and outbound API | No project |  |  | cannot
68 | Alif bank inbound API | [2204-04] Alif Bank API |  |  | can
69 | IME London inbound and outbound API | No project |  |  | cannot
70 | Alipay inbound API | No project |  |  | cannot
71 | Truemoney outbound API | No project |  |  | need check spec
72 | Upticon inbound and outbound API | No project |  |  | need check spec
73 | ACEmoney inbound API | No project |  |  | need check spec
74 | RIA inbound API for C2C |  |  |  | need check spec
75 | Terrapay inbound API | No project |  |  | need check spec
76 | 9pay outboud and inbound API | No project for outbound |  |  | need check spec
77 | Sendmn inbound API | New type inbound version 2 |  |  | need check spec
78 | Pingpong Card Payment API |  |  |  | need check spec
79 | AYA bank API |  |  |  | need check spec
80 | CB bank other bank API |  |  |  | need check spec
81 | India direct partner API |  |  |  | need check spec
82 | JME inbound and outbound API |  |  |  | need check spec
83 | Online Handphone sales using GME app |  |  |  | cannot
84 | Explanation and guide to error messages |  |  |  | cannot
85 | Wallet topup using KFTC | Project not created |  |  | can
86 | LY Hour Cash Payment for KHR Payout | Project not created |  |  | can
87 | Bangkok Bank API |  |  |  | need check spec
88 | TazaPay c2c API |  |  |  | need check spec
89 | B2B Paynoeer API |  |  |  | need check spec
90 | B2B Ebury API |  |  |  | need check spec
91 | B2B Partner 1 API |  |  |  | need check spec
92 | B2B Partner 2 API |  |  |  | need check spec
93 | B2B Partner 3 API |  |  |  | need check spec
94 | Tranglo API in New Architecture |  |  |  | need check spec
95 | Dutch Bangla API in new Architecture |  |  |  | need check spec
96 | Payform Inbound and Outbound API |  |  |  | need check spec
97 | Allow Customer to send money and put fixed deposit in their country. |  |  |  | cannot
98 | Airticket by powercall |  |  |  | cannot
99 | Multi currency wallet |  |  |  | cannot