## Time Chart
Color Code
Grey color : completed project
Green Color with in timeline
Red color : behind timeline
Sprint Timeline Detail
Task No. |  |  | Start Date | End Date | Total No Of Working Days
| GME Mobile App Sprint 2 | Incentive | 2018-11-06 | 2019-04-23 | 24 weeks
1 | Creating document format for multi language translate |  | 2018-11-06 | 2018-11-13 | 5
2 | Auto Refund Module | KRW 0.3 Mil | 2018-11-15 | 2018-11-21 | 5
3 | Penny Test Module | KRW 0.5 Mil | 2018-11-22 | 2018-11-30 | 7
4 | Auto Update Feature | None | 2018-12-03 | 2018-12-05 | 3
5 | Testing And Publish |  | 2018-12-05 | 2018-12-10 | 4
6 | KFTC Module | KRW 1 Mil | 2018-12-11 | 2019-01-09 | 21
7 | KFTC Security Keypad (Integration document to be provided on last week of december) |  | 2019-01-10 | 2019-01-16 | 5
8 | KFTC Functional And Security Test |  | After completion of KFTC Testing (Dependency)
9 | Publish |  | Jan 17, 2019 | Feb 16, 2019 | 30( Provided KFTC completes the testing within 30 days0
10 | Multi Language Support Module(9 language) | KRW 0.5 Mil | 2019-01-17 | 2019-03-14 | 15 days for setup + (3 days per language)+KFTC Support(3 days)=42
11 | Testing And Publish |  | 2019-03-12 | 2019-03-14 | 3
12 | Resend Module | KRW 1 Mil | 2019-03-15 | 2019-04-04 | 15
6 | Push Notification | KRW 0.3 Mil | 2019-04-05 | 2019-04-18 | 10
9 | Publishing/Deployment | None | 2019-04-19 | 2019-04-23 | 3
10 | Support Newly Released App | None
| Inbound Remittance(By MAX) |  | 2019-01-03 | 1/31/2019(?) | Not Planned
11 | Reward Point Module |  |  |  | Not Planned
12 | Social Wall Module |  |  |  | Not Planned
13 | API for November, 4 partners on November | KRW 0.5 Mil
14 | API for Dececmber 2 Partners + Khan Bank , K Bank , CB Bank, Islami Bank, NBP Pakistan, True Money, Wing | KRW 1 Mil
* Incentive will be release after TAX deduction
Task No. |  |  | Start Date | End Date | Total No Of Working Days
| GME Mobile API Sprint 2 | Incentive | 2018-11-06 | 2019-04-23 | 14 weeks
1 | Auto Refund Module |  | 2018-11-15 | 2018-11-20 | 4
2 | Penny Test Module |  | 2018-11-21 | 2018-11-29 | 6
3 | Auto Update Feature |  | 2018-12-03 | 2018-12-05 | 3
4 | Testing And Publish |  | 2018-12-05 | 2018-12-10 | 4
5 | KFTC Module |  | 2018-12-11 | 2019-01-07 | 19
7 | KFTC Functional And Security Test |  | After completion of KFTC Testing (Dependency)
8 | Publish |  | Jan 17, 2019 | Feb 16, 2019 | 30( Provided KFTC completes the testing within 30 days0
9 | Multi Language Support Module(9 language) |  | 2019-01-17 | 2019-02-20 | 5 days for setup + (3 days per language)+KFTC Support(3 days)=27
10 | Testing And Publish |  | 2019-03-12 | 2019-03-14 | 3
11 | Resend Module |  | 2019-03-15 | 2019-04-02 | 13
12 | Push Notification |  | 2019-04-05 | 2019-04-17 | 10
13 | Publishing/Deployment |  | 2019-04-19 | 2019-04-23 | 3
Task No. | * API deadline will be changed on priority of Business |  | Start Date | End Date | Total No Of Working Days
| GME Core API Sprint 2 | Incentive | 2018-11-15 | 2019-04-17 | 35 Weeks
1 | Mobile API v.2 |  | 2018-11-15 | 2019-04-17 | 105
2 | SBR - Vietnam |  | 2018-10-01 | 2018-11-12 | 31
3 | Dutch Bangla |  | 2018-10-05 | 2018-11-20 | 33
4 | RIA |  | 2018-10-15 | 2018-11-27 | 32- Actual working Days = 15
5 | Mongolia MNT Cash/Bank Real Time Transaction |  | 2018-11-02 | 2018-12-06 | 25
6 | X Press Money |  | 2018-11-12 | 2018-12-14 | 25
7 | True Money |  | 2018-11-20 | 2018-12-27 | 27
8 | NBP Pakistan (Agreement Signed)
9 | Islami Bank Bangladesh(Agreement Signed)
10 | Agrani Bank Bangladesh (Agreement Signed)
11 | Wing New API (Agreement Signed)
12 | Cebuana (Agreement Signed)
13 | Prime Bank ( Agreement not yet Signed)
14 | K-Bank(Agreement not yet Signed)
15 | CB Bank Myanmar(Agreement not yet Signed)
16 | Khan Bank Mongolia(Agreement not yet Signed)
17 | EXIM Bank Vietnam(Agreement not yet Signed)
18 | Transferto (Agreement not yet Signed)
Task No. | * Development Deadline will be changed on priority of Business |  | Start Date | End Date | Total No Of Working Days
| GME Online Sprint 1118 | Incentive | 2018-11-06 | 2018-12-27 | 10 Weeks
1 | SBR - Vietnam |  | 2018-11-06 | 2018-11-12 | 5
2 | Dutch Bangla |  | 2018-11-15 | 2018-11-20 | 4
3 | BNI logo support on Page |  | 2018-11-15 | 2018-11-23 | 7
4 | RIA |  | 2018-11-15 | 2018-11-27 | 8
5 | Mongolia MNT Cash/Bank Real Time Transaction |  | 2018-11-14 | 2018-12-06 | 17
6 | X Press Money |  | 2018-12-03 | 2018-12-14 | 12
7 | True Money |  | 2018-12-12 | 2018-12-27 | 12
8 | NBP Pakistan (Agreement Signed)
9 | Agrani Bank Bangladesh (Agreement Signed)
10 | Islami Bank Bangladesh(Agreement Signed)
11 | Wing New API (Agreement Signed)
12 | Cebuana (Agreement Signed)
13 | Prime Bank ( Agreement not yet Signed)
14 | K-Bank(Agreement not yet Signed)
15 | CB Bank Myanmar(Agreement not yet Signed)
16 | Khan Bank Mongolia(Agreement not yet Signed)
17 | EXIM Bank Vietnam(Agreement not yet Signed)
18 | Transferto (Agreement not yet Signed)
Task No. | * Development Deadline will be changed on priority of Business |  | Start Date | End Date | Total No Of Working Days
| GME Core Sprint 1118 | Incentive | 2018-11-06 | 2018-12-27 | 10 Weeks
1 | Modification on Profit Loss |  | 2018-11-05 | 2018-11-12 | 6 - Actual working Days =3
2 | SBR - Vietnam Settlement - FX Gain Loss/Transaction Voucher |  | 2018-11-06 | 2018-11-12 | 5 Actual working Days =2
3 | Auto debit Cancel Txn Auto Refund |  | 2018-11-12 | 2018-11-13 | 2
4 | Customer Wallet Statement |  | 2018-11-15 | 2018-11-16 | 2
5 | RIA Settlement - FX Gain Loss/Transaction Voucher |  | 2018-11-26 | 2018-11-27 | 2
6 | Dutch Bangla Settlement - FX Gain Loss/Transaction Voucher |  | 2018-11-19 | 2018-11-20 | 2
7 | Mongolia MNT Cash/Bank Real Time Transaction Settlement - FX Gain Loss/Transaction Voucher |  | 2018-12-03 | 2018-12-06 | 3
8 | X Press Money Settlement - FX Gain Loss/Transaction Voucher |  | 2018-12-12 | 2018-12-14 | 2
9 | True Money Settlement - FX Gain Loss/Transaction Voucher |  | 2018-12-24 | 2018-12-27 | 3
10 | NBP Pakistan (Agreement Signed)
11 | Islami Bank Bangladesh(Agreement Signed)
12 | Agrani Bank Bangladesh (Agreement Signed)
13 | Wing New API (Agreement Signed)
14 | Cebuana (Agreement Signed)
15 | Prime Bank ( Agreement not yet Signed)
16 | K-Bank(Agreement not yet Signed)
17 | CB Bank Myanmar(Agreement not yet Signed)
18 | Khan Bank Mongolia(Agreement not yet Signed)
19 | EXIM Bank Vietnam(Agreement not yet Signed)
20 | Transferto (Agreement not yet Signed)

## Penny Test Module
Penny Test Module
S/No | Activity | Details | Start | End
1 | Planning | Penny test flow planning in the mobile application | 2018-11-15 | 2018-11-16
API Endpoint (Request/Response Json) planing for penny test operation
2 | Development | Design and develop UI Form to perform Penny test | 2018-11-17 | 2018-11-21
Integrate the Penny test form to existing KYC registration module without breaking the flow. So that the penny test is performed just prior to performing KYC form submission.
Create Network Layer for penny test to perform api integration with server
Network Layer developed to carryout the following operation - Submiting form data for penny test - if error show error else submit kyc form - handle kyc form submit or error
3 | Testing (White Box Testing by Developers) | Created mocked test for following api - Penny test submit apii UI/UX testing Validation Testing Penny test integration testing with existing flow | 2018-11-22 | 2018-11-23
Kyc Submit Process before Penny test
Kyc Submit Process After Penny Test

## Auto Refund Module
Auto Refund Module
S/No | Activity | Details | Start | End
1 | Planning | Plan and design UI Forms for auto refund process. | 2018-11-26 | 2018-11-26
API Endpoint (Request/Response Json) planing for auto refund operation.
2 | Development | Develop UI Form to perform Auto Refund operation | 2018-11-27 | 2018-11-29
Create Network Layer for api integration to perform auto refund operation, which carry out the following operation: - Send auto refund transaction - Perform server side validation - Fetch user related data again after transaction sucessfull.
Show error correspondingly if validation fails otherwise redirect to dashboard and fetch user related data again to update user balance in dashboard.
3 | Testing (White Box Testing by Developers) | Creat mocked test for following scenario - UI navigation flow - Servier side validation fail resposne - Update user balance after successfull transation - Receipt api - Account validation api UI/UX testing | 2018-11-30 | 2018-11-30

## KFTC Module
KFTC Module
S/No | Activity | Details | Start | End
1 | Planning | Study the SDK documentation provided by third party for the KFTC integration in the app | 2018-12-03 | 2018-12-05
Planning UI Forms for Auto Debit account CRUD operation - Form to list all registered auto debits accounts to the user - Form to register new auto debit account to the user - Form to modify/delete existing auto debit account to the user
Planning UI Forms for Auto Debit transaction operation - R & D for virtual keyboard integration during password prompt for security purpose.
Reiterate the flow of send money module again
Planning Integration of KFTC Module as a part of send money transaction
API Endpoint (Request/Response Json) planning for Auto Debit transaction operation including otp validaiton api.
API Endpoint (Request/Response Json) planning for Auto Debit CRUD operation - Fetch all Auto Debit accounts registered to the user - Add new auto debit accounts to the user - Modify Existing auto debit accounts registered to the user - Delete the the exsiting auto debit accounts registered to the user
2 | Development | Design and develop UI Form to perform Auto Debit Account CRUD operations: - Show all registered auto debits accounts to the user - Register new auto debit accounts to the user - Modify the existing auto debit account by the user | 2018-12-06 | 2018-12-27
Revamp the existing send money module to allow user to select auto debit account from their list and perform transaction using either their pin code or password after OTP validation.
Provide in-app virtual keyboard to mitigate security issue
Develop Network Layer to carryout the following operation needed for KFTC module - SDK Integration provided by third party - Create API Integration with server for auto debit account CRUD Operation - Add/Register new auto debit account - Modify existing auto debit account - Delete existing auto debit account - Perform API Validation
3 | Testing (White Box Testing by Developers) | Created Mock test for following operation - Payment mode selection api - Ex rate calculator api - Transaction Confirmation api - Receipt api - Account validation api UI/UX testing Send Money overall testing OTP Validation Testing | 2018-12-28 | 2018-12-31

## Multi Language
Multi Language Module
S/No | Activity | Details | Start | End
1 | Planning | Revamp Splash screen to accomodate localization | 2018-01-01 | 2019-01-04
Plan the localization of app
Sort out all the hardcoded words used within the application. (android and ios)
Create a list of all word to be translated in the excel sheet and distribute it to all members for translation
2 | Development | Perform Localization: - Refactor existing hardcorded text used in the app. - Provide word by word (1 - n) mapping of each translated word within the app. - Create association of each translated word to the respective view element. - Finally generate Locale configuration that can be changed dynamically. - Select Locale using user native country. Adjust overall app font design to respective to different language | 2019-01-07 | 2019-02-07
Create UI for user language selection
Change the flow of splash screen to prompt selection of language
3 | Testing (White Box Testing by Developers) | Mock Localization UI/UX testing Multiple device locale compatiblity testing | 2019-02-08 | 2018-02-11

## Push Notifications
Push Notification Module
S/No | Activity | Details | Start | End
1 | Planning | Plan on integration of Firebase Push Notification system | 2019-02-12 | 2019-02-13
Plan the flow of in-app notification management.
Plan and design the custom view for showing in-app notificaiton
Plan API Endpoint for fetching the history of sent push notification to the user
2 | Development | Integrate Firebase push notification in the app | 2019-02-14 | 2019-02-21
Integrate Firebase push notification to the GME Remit Server
Design and develop custom view for displaying in-app notification to the user
Design and develop UI Form for showing the history of sent push notification to the user
3 | Testing (White Box Testing by Developers) | API Integration testing with Firebase Server and GME Remit Server UI/UX testing of in-app push notification | 2019-02-22 | 2019-02-25

## Resend Module
Resend Feature In Send Money Module
S/No | Activity | Details | Start | End
1 | Planning | Plan resend money without breaking existing send money flow | 2019-02-26 | 2019-03-01
Plan for modification of existing API integration in send money
Desing new UI form to list transaction history for the accomodation of resend feature in send money
2 | Development | Design and develop UI forms: - Reciever recent transaction history - Exchange Rate calculation page | 2019-03-04 | 2019-03-13
Integrating to existing send money with auto debit feature
Design and develop custom view for displaying in-app notification to the user
Design and develop UI Form for showing the history of sent push notification to the user
3 | Testing (White Box Testing by Developers) | API Integration testing | 2019-03-14 | 2019-03-18